## Sheet1
Number | Task | Start Date | End Date | Completed | December |  |  | January |  |  |  | February |  |  | March | [7 empty] | April
[5 empty] | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 18 | 24 | 28 | 1 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 4
1 | Review of Literature, Identification of Problems, Team Creation | 2024-12-26 | 2024-12-28 | 100%
2 | Creation of Abstract | 2025-01-01 | 2025-01-04 | 100%
3 | Preparation of Software Requirements Specification Document | 2025-02-18 | 2025-02-18 | 100%
4 | Creation of Software Design Document | 2025-02-24 | 2025-02-24 | 100%
4.1 | System Architecture Design | 2025-02-24 | 2025-02-24 | 100%
4.2 | Application of Architecture Design | 2025-02-24 | 2025-02-24 | 100%
4.3 | Frontend Design | 2025-02-24 | 2025-02-24 | 100%
4.4 | Database Design | 2025-02-24 | 2025-02-24 | 100%
4.5 | Technology Stack | 2025-02-24 | 2025-02-24 | 100%
5 | Test plan, Test case, Traceability matrix | 2025-02-28 | 2025-03-01 | 100%
6 | Creation of Project Plan | 2025-03-01 | 2025-03-01 | 100%
7 | Development | 2025-03-17 | 2025-03-22 | 100%
7.01 | Set coding standards | 2025-03-17 | 2025-03-17 | 100%
7.02 | Environment Setup | 2025-03-17 | 2025-03-17 | 100%
7.03 | Source code control setup | 2025-03-18 | 2025-03-18 | 100%
7.04 | Development | 2025-03-19 | 2025-03-22 | 100%
7.05 | Unit Testing | 2025-03-23 | 2025-03-23 | 100%
7.06 | Integration Testing | 2025-03-23 | 2025-03-23 | 100%
7.07 | Testing Quality Assurance | 2025-03-23 | 2025-03-23 | 100%
7.08 | Functional Testing | 2025-03-23 | 2025-03-23 | 100%
7.09 | Load testing | 2025-03-23 | 2025-03-23 | 100%
7.10 | Report bugs | 2025-03-23 | 2025-03-23 | 100%
7.11 | Resolve bugs and Retest | 2025-03-23 | 2025-03-23 | 100%
8 | Deployment | 2025-03-23 | 2025-03-23 | 100%
9 | Final Project Report | 2025-03-04 | 2025-03-04 | 100%